|  | Project Charter |
| --- | --- |

Project Name: Maternity Stream System (MSS) — Pilot Project

Organization: Maternity Stream International

Description: The Maternity Stream System (MSS) is a Healthcare SaaS Pilot Project for Maternity Stream International (MSI), delivering telehealth, pathology, imaging, and pharmacy services to expectant mothers across Perth, Rockingham, and Mandurah — including regional, Aboriginal, and CALD communities. The project comprises three sub-projects: MSS software development (Sub-Project I), network and infrastructure rollout (Sub-Project II), and data migration (Sub-Project III), to be delivered as a one-year Pilot ahead of potential wider rollout.

Created By: Student Vaasu Goyal (35844851)

Table of Contents

1	General Project Information	3

2	Project Scope Statement	3

3	Cost Estimate	4

4	Project Timeline	4

5	Project Stakeholders	5

6	Project Ethical and Sustainability Considerations	5

7	Assumptions, Constraints, and Potential Risk	7

8	Sign-Off	7

9	Definitions and Acronyms	8

General Project Information

| Project Name: | Maternity Stream System (MSS) — Pilot Project |
| --- | --- |
| Project Sponsor: | Ben Dover (CIO) |
| Project Lead: | Vaasu Goyal |
| Contact Email: | 35844851@student.murdoch.edu.au |

Project Scope Statement

| Business Case: | · Addresses a real access gap: regional/remote WA mothers, Aboriginal and CALD communities lack equitable access to maternity specialists · Aligns with WA Health / WA Country Health Service strategic priority on regional access · Opens new SaaS revenue stream for MSI beyond its current WA Health service delivery focus · Positions MSI for expansion into other Australian markets if pilot succeeds · Financially justified by ROM figures: revenue overtakes costs by Year 2 ($1.12M benefits vs $420K costs) |
| --- | --- |
| Project Description: | · Problem: fragmented, travel-dependent maternity care across Perth/Rockingham/Mandurah; siloed pathology/imaging/pharmacy/telehealth workflows · Cause: no unified digital platform connecting these four services or supporting remote access · Proposed solution: Healthcare SaaS platform (MSS) unifying telehealth, scheduling, billing, analytics, and health info exchange · Feasibility: leverages WA's existing network infrastructure; SaaS model minimizes upfront capital cost; phased as a 1-year Pilot Project before full rollout · Expected outcome: stable, secure, scalable, user-friendly maternity platform live across all 3 sites by May 2027 |
| Objectives: | · Deliver a working MSS Pilot Project covering pathology, imaging, pharmacy and telehealth by 05 May 2027 (Go-Live) · Achieve Board approval / Stage Gate sign-off on the Project Charter by 25 May 2026 · Complete provider/vendor RFT engagement by 01 Jun 2026 · Achieve positive NPV within the 4-year ROM projection window · Deliver quarterly usable feature releases across the 12-month software development period · Complete Pilot Project closure and lessons-learned reporting by 27 Aug 2027 |
| Scope: | - In-Scope: - 1. Design and development of a cloud-based Healthcare SaaS platform (MSS) with modules for telehealth, appointment scheduling, billing/claims processing, health data analytics, and pathology/imaging/pharmacy information exchange (Sub-Project I) - 2. Assessment of current network capacity and infrastructure gaps across Perth, Rockingham, and Mandurah (Sub-Project II) - 3. Design, installation, and commissioning of network and IT infrastructure across all three sites (Sub-Project II) - 4. Mapping, cleansing, migration, and reconciliation of existing patient and clinical data into the MSS platform (Sub-Project III) - 5. Engagement of a Healthcare SaaS vendor and third-party technical contractors through a formal RFT process - 6. Integration of MSS with a Healthcare Service Bus (HCB) and API Gateway to support interoperability with existing EHR, LIS, and PACS systems - 7. Implementation of Identity and Access Management (IAM) and Multi-Factor Authentication (MFA) for secure platform access - 8. Conduct of User Acceptance Testing (UAT) and go-live readiness assessment across all three sites - 9. Delivery of training, communications, and operational handover activities to support MSI's ongoing management of MSS - Out-of-Scope: - 1. Expansion of MSS services beyond the three current MSI sites (Perth, Rockingham, Mandurah) - 2. Extension of MSS functionality to non-maternity health services - 3. Development of features beyond the four core services (pathology, imaging, pharmacy, telehealth) during the Pilot (e.g. AI diagnostics will not be included) - 4. Formal scaling of MSS to other Australian states or markets (to be considered only if the Pilot succeeds; not part of this Charter) - 5. Ongoing production support and maintenance beyond the Pilot Project Closure date (27 Aug 2027 |
| Deliverables: | Sub-Project I — Systems Implementation (Agile): 1. A functional, secure, cloud-based Healthcare SaaS platform (MSS) covering telehealth, scheduling, billing, analytics, and health information exchange 2. A prioritized product backlog and quarterly working software increments 3. UAT test results and sign-off for the MSS software Sub-Project II — Network & Infrastructure (Plan-Driven): 4. Installed, configured, and commissioned network and IT infrastructure across Perth, Rockingham, and Mandurah 5. Network architecture and infrastructure design documentation (logical and physical) 6. A post-implementation monitoring report for network infrastructure Sub-Project III — Data Migration (Plan-Driven): 7. Migrated, cleansed, and reconciled patient and clinical data within the production MSS environment 8. A signed data migration reconciliation and sign-off report Cross-Project / Management: 9. Signed contracts with the selected Healthcare SaaS vendor and third-party providers 10. An approved Project Charter and supporting business case documentation 11. Training materials and operational support guides for MSI staff 12. A formal Pilot Project Closure Report with lessons learned and benefits tracking |

Cost Estimate

| Cost estimate | The MSS Pilot Project's financial viability was assessed using the ROM Costs/Expenditures and ROM Benefits/Revenues provided in the Project Scenario Description, discounted at a combined rate of 7.8% (3% inflation + 4.8% cost of capital/interest rate on the project loan), in line with the assumptions stated in the scenario. The analysis produces a positive NPV, a payback period within the project's early years, and an ROI indicating the project is expected to return significantly more value than it costs. On this basis, the project appears financially viable and worth recommending to the Board for approval, though as ROM estimates carry a stated variance of 25–40%, these figures should be treated as directional rather than final. |
| --- | --- |

| Description | Year 0 | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- | --- |
| Discounted ROM Costs/Expenditures | $705,000 | $548,700 | $361,200 | $288,000 | $1,902,900 |
| Discounted ROM Benefits/Revenues | $256,000 | $757,950 | $963,200 | $1,064,800 | $3,041,950 |
| Expected NPV adjusted Profit/Loss | -$449,000 | $209,250 | $602,000 | $776,800 | $1,139,050 |

| NPV | ≈ $1,139,050 |
| --- | --- |
| ROI | ≈ 60% (discounted total benefit $3,041,950 vs. discounted total cost $1,902,900) |
| Payback Period | ≈ 2 year, 4 months (cumulative discounted cash flow turns positive partway through Year 2) |

Project Timeline

| Project Time | Start Date: 01 June 2026 Expected End Date: 27 August 2027 |
| --- | --- |
| Progress Milestones: | Date; Milestone; Source. 01 Mar 2026; Preparations Commence — informal stakeholder/contractor relationship-building; Board materials (incl. Project Charter) developed; Given. 13 Apr 2026; Submission to the Board — project materials submitted for approval decision; Given. 25 May 2026; Board Approval — Stage Gate approval for Project Charter/Business Case; Given. 01 Jun 2026; Formal Project Start Date — project funds formally allocated; Given. 01 Jun 2026; Engage Providers — RFT process to select SaaS vendor and contractors; Given. 15 Jun 2026; Commence MSS Software Development (Sub-Project I) — agile development begins; Given. 01 Jul 2026; Product Backlog finalized in Azure DevOps — 25 prioritized user stories scoped across six 2-week sprints (Sprint 1–6, 15 Jun–6 Sep 2026); Added. 15 Sep 2026; First Quarterly Release — All Now-phase capabilities usable: core consultation and clinical access (telehealth, EHR, scheduling, e-prescription, lab alerts), security and identity foundations, patient self-service, billing and claims, pharmacy inventory, clinician/admin operational views, and telehealth video delivery; Added. 15 Dec 2026; Second Quarterly Release — Integration and Hardening — formal end-to-end integration testing, performance validation, and stabilisation across all Now-phase MSS modules ahead of full-service expansion; Added. 01 Dec 2026; Stage Gate Approval for Sub-Projects II and III Execution Phase; Given. 01 Feb 2027; Data Migration Completed and Validated (Sub-Project III); Added. 15 Mar 2027; Third Quarterly Release — Full pathology, imaging and pharmacy information exchange integration complete; Added. 26 Mar 2027; Network and Infrastructure Installation and Commissioning (Sub-Project II); Given. 05 Apr 2027; UAT Sign-off completed across all three sites; Added. 05 May 2027; Go-Live Approval — hard-wall milestone; all services live and stable; Given. 27 Aug 2027; Formal Pilot Project Closure — final reports and deliverable submitted; Given. |

Project Stakeholders

| Stakeholder | Interest/Expectations |
| --- | --- |
| 1.Ben Dover (CIO & Project Sponsor) | • Accountable for project budget and strategic direction • Expects regular progress updates and to be consulted on key decisions • Directly impacted if the project fails to deliver value or exceeds cost estimates |
| 2. Dr Sara Adams (Product Manager) | • Works directly with the Product Owner to shape product strategy and roadmap • Expects the delivered software to align with organizational goals and user needs • Reports progress up to the CIO, so is affected by delivery delays or scope issues |
| 3.Clinicians (midwives, obstetricians, radiologists, pathologists, pharmacists, telehealth providers) | • Primary domain experts and day-to-day users of the MSS platform • Interested in whether the system genuinely supports clinical workflows and terminology • Directly affected by poor usability, which could disrupt patient care delivery |
| 4.Expectant Mothers (incl.remote, Aboriginal and CALD communities | • End beneficiaries of the platform; primary reason the project exists • Expect improved access to maternity services without excessive travel • Significantly affected by accessibility, cultural appropriateness, and ease of use of the system |
| 5.WA Health / WA Country Health Service | • External strategic partner with interest in equitable regional healthcare access • Expects the project to align with broader public health objectives • Affected reputationally and strategically if the pilot succeeds or fails, given implications for future funding/partnership |

Project Ethical and Sustainability Considerations

| Checklist of Ethical/Sustainability Issues | Does the Project pose an Ethical/Sustainability Issue related to this dimension? (Y/N) (If Yes, State the potential issue) | Which Stakeholders are affected? | Alternative course of action | Relevant laws, ethical principles, and codes of ethics, or sustainability frameworks that apply |
| --- | --- | --- | --- | --- |
| System Quality and Reliability |  |  |  |  |
| Data Protection and Privacy | Y - MSS stores highly sensitive patient health data (pathology, imaging, medication history) on a third-party SaaS platform, raising risk of unauthorized access or misuse | Expectant mothers, clinicians, MSI | Enforce encryption in transit/at rest, strict role-based access control, and mandatory privacy compliance audits of the chosen SaaS vendor before contract signature | Australian Privacy Principles (APPs); Privacy Act 1988 (Cth) |
| Transparency and accountability |  |  |  |  |
| Diversity and inclusivity | Y — a generic system design may not account for the cultural, linguistic, or communication needs of Aboriginal and CALD communities | CALD and Aboriginal mothers, patient advocates | Co-design patient-facing features with patient advocates and cultural liaison input; provide multilingual support | WA Health cultural safety frameworks; principle of culturally appropriate care |
| Fairness and Equity | Y — a digital-first platform risks excluding patients with limited digital literacy, connectivity, or device access, particularly in regional/remote areas | Regional and remote expectant mothers, Aboriginal patients | Maintain phone/in-person fallback channels alongside MSS rather than replacing them outright | WA Country Health Service equity objectives; principle of equitable access to healthcare |
| Security and Compliance | Y - as a cloud-hosted healthcare system, MSS is a target for cyberattack; a breach could expose clinical data or disrupt patient care | Patients, clinicians, MSI, WA Health | Require security certification and penetration testing of the SaaS provider prior to go-live; engage Don Morrison (Security & Compliance Expert) throughout design | APPs; HL7 and FHIR healthcare data standards; MSI's regulatory compliance obligations to WA Health |
| Social and Environmental Responsibility |  |  |  |  |

Assumptions, Constraints, and Potential Risk

| Assumptions: | · The selected Healthcare SaaS vendor will be able to meet HL7 and FHIR compliance standards within the contracted timeframe · Network infrastructure in Rockingham and Mandurah is adequate, or can be upgraded within the allocated budget, to support the platform · Contractors and third-party specialists (StreamTech, DCPlus, DemSet) will have capacity to engage once formally selected via the RFT process · WA Health will continue to support and, where relevant, co-fund the initiative throughout the Pilot Project · Clinicians and administrative staff will be available for user story validation, UAT, and workflow consultation as needed · Expectant mothers across all three regions will have sufficient access to internet-connected devices to use the platform |
| --- | --- |
| Potential Constraint: | · The Go-Live date of 05 May 2027 is a Board-identified hard-wall milestone and cannot be moved · Project funding is limited to a fixed bank loan (4.8% p.a.) with no additional equity or grant funding available · The Pilot Project is limited in scope to three sites only (Perth, Rockingham, Mandurah) and four core services (pathology, imaging, pharmacy, telehealth) · All patient data handling must comply with strict Australian healthcare privacy regulation, limiting vendor and architecture choices · The Product Owner role covers only Sub-Project I (software); Sub-Projects II and III (infrastructure and data migration) run on a shared timeline requiring cross-team coordination |
| Potential Risks: | · The selected SaaS vendor fails to meet healthcare compliance or security standards, delaying development or go-live · Actual project costs exceed the ROM estimates beyond the stated 25–40% variance, straining the fixed loan-based budget · Low digital adoption among target patient groups (particularly regional, Aboriginal, and CALD communities) undermines the platform's value case · Data migration errors in Sub-Project III compromise the integrity of migrated clinical data · Delays from third-party contractors or providers cascade into missed quarterly release milestones · Network/infrastructure commissioning in Sub-Project II is delayed, jeopardising the fixed Go-Live date |

Sign-Off

|  | Name | Signature | Date (dd/mm/yyyy) |
| --- | --- | --- | --- |
| Project Sponsor | Ben Dover |  |  |
| Senior Executive | Dr Donna Jenner |  |  |
| Project Lead | Vaasu Goyal |  |  |
| Notes: |  |  |  |

Definitions and Acronyms

API Gateway — a secure, controlled entry point for external access to MSS data and functionality, enabling integration with other healthcare systems (e.g. EHRs) while maintaining regulatory compliance

APP — Australian Privacy Principles

CALD — Culturally and Linguistically Diverse

CEO — Chief Executive Officer

CIO — Chief Information Officer

CIS — Clinical Information System — a computer-based system for collecting, storing, and managing patient data to support point-of-care decisions

Data Bus — links disparate data sources, performs consolidation/federation, and provides a unified data model to the Healthcare Service Bus

EHR — Electronic Health Record

EMM — Enterprise Mobility Management — securing and managing mobile devices, applications, and content used for telehealth and remote work

EULA — End User License Agreement

Event Queue — stores generated system events (e.g. record updates, lab results, logins) in order for asynchronous processing, decoupling event generation from processing

FHIR — Fast Healthcare Interoperability Resources — a standard for electronic healthcare information exchange

HCB — Healthcare Service Bus — a central communication hub (built on an enterprise service bus) enabling integration between systems like EHRs, LIS, and PACS

HL7 — Health Level Seven — international standards for transferring clinical and administrative health data

IAM — Identity and Access Management — controls user identity and system access, integrating with systems like LDAP, Active Directory, or OAuth 2.0

LIS — Laboratory Information System

MFA — Multi-Factor Authentication — requires multiple forms of authentication (e.g. password + SMS code) for added security

MSI — Maternity Stream International Pty Ltd

MSS — Maternity Stream System

NPV — Net Present Value

PACS — Picture Archiving and Communication System — used for sharing medical imaging

PO — Product Owner

QA — Quality Assurance

RFT — Request for Tender

ROI — Return on Investment

ROM — Rough Order of Magnitude

SaaS — Software as a Service

Security Gateway — provides access control for data, granting/revoking permissions so sensitive records are only visible to authorised users

SLA — Service Level Agreement — commitments from the SaaS provider on system uptime and reliability

SME — Subject Matter Expert

SSO — Single Sign-On

UAT — User Acceptance Testing

WA Health — Western Australia Department of Health

WACHS — WA Country Health Service

END OF DOCUMENT